## Procurement Log
CSI Division | Scope / Package | Material / Item | Specification | Quantity | Unit | Budget Unit Cost ($) | Total Budget ($) | Potential Vendors | Assigned To | Procurement Status | Lead Time (weeks) | Required On Site Date | Submittal Required | Notes
03 30 00 | Foundations | Concrete (4000 PSI) Variant 1 | ASTM C94 | 1200 | CY | 180 | 216000 | CEMEX; CalPortland | PE1 | Bidding | 3 | 2026-06-15 | Yes | Mix design approval needed
03 20 00 | Reinforcement | Rebar Variant 2 | Grade 60 | 150 | tons | 900 | 135000 | CMC; Gerdau | PE1 | Bidding | 4 | 2026-06-10 | Yes
05 12 00 | Structural Steel | Wide Flange Beams Variant 3 | A992 | 200 | tons | 2500 | 500000 | Nucor; SteelFab | PM | RFQ Sent | 8 | 2026-07-01 | Yes
05 31 00 | Decking | Metal Deck Variant 4 | 1.5" Composite | 50000 | SF | 3.5 | 175000 | Verco; Vulcraft | PE2 | Bidding | 5 | 2026-07-10 | Yes
06 10 00 | Rough Carpentry | Wood Blocking Variant 5 | KD Lumber | 2000 | BF | 4 | 8000 | Home Depot; 84 Lumber | PE3 | Planned | 2 | 2026-07-20 | No
07 21 00 | Thermal Insulation | Rigid Insulation Variant 6 | R-20 | 10000 | SF | 2.5 | 25000 | Owens Corning; Dow | PE2 | Bidding | 3 | 2026-08-01 | Yes
07 27 00 | Air Barrier | Fluid Applied Membrane Variant 7 | ASTM E2357 | 8000 | SF | 4 | 32000 | Henry; Tremco | PE2 | Planned | 3 | 2026-08-05 | Yes
07 54 00 | Roofing | TPO Membrane Variant 8 | 60 mil | 12000 | SF | 6 | 72000 | Carlisle; Firestone | PM | RFQ Sent | 6 | 2026-08-15 | Yes
08 11 13 | Doors | Hollow Metal Doors Variant 9 | 16 gauge | 50 | EA | 400 | 20000 | Ceco; Steelcraft | PE3 | Bidding | 5 | 2026-08-20 | Yes
08 14 16 | Doors | Wood Doors Variant 10 | Solid Core | 60 | EA | 350 | 21000 | VT Industries; Masonite | PE3 | Planned | 4 | 2026-08-25 | Yes
08 71 00 | Hardware | Door Hardware Sets Variant 11 | ANSI Grade 1 | 110 | EA | 250 | 27500 | Assa Abloy; Allegion | PE3 | Planned | 3 | 2026-09-01 | Yes
09 21 16 | Framing | Metal Stud Framing Variant 12 | 25 gauge | 30000 | LF | 2 | 60000 | ClarkDietrich; Marino | PE2 | Bidding | 4 | 2026-09-10 | No
09 29 00 | Drywall | Gypsum Board Variant 13 | 5/8" Type X | 50000 | SF | 1.2 | 60000 | USG; National Gypsum | PE2 | Bidding | 3 | 2026-09-15 | No
09 51 00 | Ceilings | ACT Ceiling Tiles Variant 14 | 2x2 | 20000 | SF | 3 | 60000 | Armstrong; USG | PE3 | Planned | 3 | 2026-09-20 | Yes
09 65 00 | Flooring | Carpet Tile Variant 15 | Commercial Grade | 15000 | SF | 4 | 60000 | Interface; Shaw | PE3 | Planned | 5 | 2026-10-01 | Yes
09 68 00 | Flooring | Resilient Flooring Variant 16 | LVT | 8000 | SF | 5 | 40000 | Tarkett; Shaw | PE3 | Planned | 5 | 2026-10-05 | Yes
09 91 00 | Painting | Interior Paint Variant 17 | Low VOC | 60000 | SF | 0.8 | 48000 | Sherwin Williams; Behr | PE2 | Planned | 2 | 2026-10-10 | No
22 11 00 | Plumbing | Domestic Water Piping Variant 18 | Copper Type L | 5000 | LF | 6 | 30000 | Mueller; NIBCO | MEP1 | RFQ Sent | 6 | 2026-07-20 | Yes
22 13 00 | Plumbing | Sanitary Piping Variant 19 | PVC | 4000 | LF | 4 | 16000 | Charlotte Pipe; JM Eagle | MEP1 | Bidding | 5 | 2026-07-25 | Yes
23 05 00 | HVAC | Ductwork Variant 20 | Galvanized Steel | 10000 | SF | 10 | 100000 | Lindab; Spiral Pipe | MEP2 | RFQ Sent | 8 | 2026-08-01 | Yes
23 07 00 | HVAC | Duct Insulation Variant 21 | R-8 | 8000 | SF | 2.5 | 20000 | Johns Manville; Owens Corning | MEP2 | Planned | 4 | 2026-08-10 | Yes
23 09 00 | Controls | Building Automation System Variant 22 | DDC Controls | 1 | LS | 150000 | 150000 | Johnson Controls; Siemens | PM | RFQ Sent | 10 | 2026-08-15 | Yes
26 05 00 | Electrical | Conduit Variant 23 | EMT | 20000 | LF | 1.5 | 30000 | Allied Tube; Wheatland | ELEC1 | Bidding | 4 | 2026-07-15 | No
26 05 19 | Electrical | Wire Variant 24 | THHN Copper | 50000 | LF | 0.5 | 25000 | Southwire; Encore | ELEC1 | Bidding | 3 | 2026-07-20 | No
26 24 16 | Electrical | Panelboards Variant 25 | 208/120V | 10 | EA | 3000 | 30000 | Square D; Eaton | ELEC1 | RFQ Sent | 6 | 2026-08-01 | Yes
26 27 26 | Electrical | Receptacles Variant 26 | Duplex | 500 | EA | 10 | 5000 | Leviton; Hubbell | ELEC1 | Planned | 2 | 2026-08-10 | No
26 51 00 | Lighting | LED Fixtures Variant 27 | Office Grade | 300 | EA | 150 | 45000 | Lithonia; Cooper | ELEC2 | RFQ Sent | 5 | 2026-08-15 | Yes
31 00 00 | Sitework | Excavation Variant 28 | Earthwork | 1 | LS | 100000 | 100000 | Local Contractors | PM | Awarded | 4 | 2026-05-20 | No
32 13 00 | Sitework | Concrete Paving Variant 29 | 6" Slab | 8000 | SF | 8 | 64000 | Local Subs | PE1 | Planned | 3 | 2026-06-01 | Yes
03 30 00 | Foundations | Concrete (4000 PSI) Variant 30 | ASTM C94 | 1200 | CY | 180 | 216000 | CEMEX; CalPortland | PE1 | Bidding | 3 | 2026-06-15 | Yes | Mix design approval needed